## 5.29
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
1 | GUI | As a customer, want a wonderful software UI, so that attract more businesses to choose | Very high | 1 | Satisfactory user interface |  | 2020.3.20 | 2020.4.2
2 | generality | As a customer, want generality，The software should be flexible and extensible， so that it can be used in a general market in the future and improve product value. | Very high | 1 | To be used in another restaurant, add dish, add payment options etc |  | 2020.3.20 | 2020.4.3
3 | Clear features | As a end user, Want to be able to operate the software with common sense or with simple instructions, so that customers know what they should do in each phase. | Very high | 1 | The function of the software is clear, the process of ordering is simple and the function is friendly. |  | 2020.3.20 | 2020.4.2
4 | Registered account | As a end user,Want a simple registration process, so that avoid disturbing customers. | high | 1 | Account registration can be completed in a very short time |  | 2020.4.3 | 2020.4.6
5 | Registered account | As a manger, want the userID , tel Num, Email to be a specific form. So that they can reduce the possibility of file errors. | high | 2 | Make sure telephone number just contain digits, name just contain English letters and Email comply with the format "xx@x.x"('x' identify one or more letters). |  | 2020.4.6 | 2020.4.17
6 | abundant dishes | As a end user，want the restaurant to Provide more ingredients, including ingredients, spicy degree, to meet the preferences of customers. so that attract customers use it. | high | 1 | Customer can choose the spicy degree, noodles and ingredients you want |  | 2020.4.3 | 2020.4.10
7 | Message Board | As a end user，want have a place to evaluate the dishes or the software, so that I can express my opinions or protect my rights. | secondary | 1 | Have a separate plate to explain the dishes |  | 2020.4.17 | 2020.4.27
8 | take-out food | As a end user，add option，Want more option like Restaurant to home. so that attract customers use it. | low | 1 | The way of eating includes taking out to home |  | 2020.4.17 | 2020.4.29
9 | ticket and order | As a end user, want to print tickets, including order information and customer information, so that help customer to make show what they’ve ordered. | Very high | 1 | Users can view their bills |  | 2020.4.17 | 2020.4.30
10 | ticket and order | As a end user, want to modify order so that improve fault tolerance. | Very high | 2 | Before payment, users can modify their own bills |  | 2020.4.20 | 2020.5.1
11 | payment option | As a end user, want a wide variety of payment methods, so that customers will feel very flexible. | high | 1 | Users can choose different payment methods |  | 2020.4.20 | 2020.5.2
12 | recommendation | As some selection difficulties, want add function --- recommendation module. It give recommendations based on the sales of the product in several week, so that help these person a lot. | secondary | 1 | Ensure customers can see the hot dishes of this week, so that they can quickly try new food collocations |  | 2020.5.1 | 2020.5.10
13 | data type | As a development member, want basic restrictions and error checking ，so that reduce software errors. | high | 1 | Make sure that all of input format correspond the requirement of specific model and wrong input need to be rewritten untill right. |  | 2020.3.20 | 2020.4.3
14 | File storage format | As a development member, want to use plain Text (txt), CSV, JSON, or XML， so that help data processing. | high | 1 | Make sure to use only TXT, thriller, CSV format in the use of the database, and make sure that the team uses unified format files for development. |  | 2020.3.20 | 2020.4.17
15 | software iteration. | As a development member, want to be capable of adapting to such future changes. so that help software iteration. | high | 1 | Ensure the stability of software development process and continuous improvement of functions. |  | 2020.3.21 | 2020.4.18
16 | Code decoupling | As a development member, want to split code into several parts that are not highly dependent, so that different members of team can develop at the same time | high | 1 | Ensure the division of labor is reasonable, team cooperation is consistent, and the interface is correct. |  | 2020.3.22 | 2020.4.19
17 | Loyalty scheme | As a mangement, want have a Loyalty scheme，count customers' consumption times and provide feedback plan, so that appear more loyal customer and improve the business | Very high | 1 | Provide more specific functions to make sure customers who login should be recorded and develop preferential policies for regular customers. |  | 2020.4.17 | 2020.5.1
18 | Loyalty scheme | As a mangement, want to visualize how many virtual stamps s/he received so far, an email and/or SMS will be sent to inform him of the number of stamps collected so far, so that attract customers | Very high | 2 | Make sure customer who have 10 stamps can pay for the bill by stamps and reduce the amount of stamps by 10 after payment. |  | 2020.5.1 | 2020.5.12
19 | Loyalty scheme | As a mangement, want more concessions， so that attract customers | high | 3 | Make sure half price on Thursday and show relevant information in the order and bill. |  | 2020.5.18 | 2020.5.22
20 | Manage ordering | As a mangement, want an independent manager interface for order and performance statistics, this is necessary | Very high | 1 | Managers has their own interface to check price and sales volume and modify the price and state of the product, especially, this part doesn’t allow customer access. |  | 2020.5.1 | 2020.5.10
21 | Food stock | As a mangement,want to manage the menu, you can modify the menu content and price (operation: add, delete, modify and check), so that the business can maintain the restaurant business. | high | 2 | Allow managers to check each ingredient in menu content and modify their state and price, besides, these information in document should be rewritten by new information. |  | 2020.5.4 | 2020.5.15
22 | Add new dishes | As a mangement,want to add new dish directly by operating software and without change txt by myself, so that I can operate it easily. | low | 3 | Ensure administrators can add new food |  | 2020.5.18 | 2020.5.25
23 | order statistics | As a mangement, want an independent manager interface for order and performance statistics, so that they can mange restaurant better. | Very high | 1 | In the GUI， manger can open the statistic menu. |  | 2020.5.4 | 2020.5.11
24 | order statistics | As a mangement,Want to manage orders, count order information, turnover and the total revenue of the week, so that facilitate the management of restaurants. | Very high | 2 | Have the function of statistics sales |  | 2020.5.12 | 2020.5.18
25 | order statistics | As a mangement,Want to know the most popular dishes of the week (Monday to Sunday) so that facilitate the management of restaurants. | Very high | 3 | According to the sales, we can get the best selling food every week |  | 2020.5.18 | 2020.5.26
26 | message board | As The active manager Want a message board that allows users to comment on dishes, management delete and reply users' comments, so that adjust the menu in time to meet customers' preferences. | secondary | 1 | Make sure to have a board to communicate with customers and leave messages. |  | 2020.5.18 | 2020.5.25
27 | equipment cost | As a technology provider, want to develop using Java as a stand-alone application. Simple graphic user interface (GUI) should be used. Latest Java SE (10 or above) should be used. So that reduce the equipment cost of managers | high | 1 | Make sure to use latest Java SE (10 or above), use relative components which development platform provides to develop GUI |  | 2020.3.20 | 2020.4.17
28 | extra app function | As a technology provider, want to limit software without the specific payment function, mail function and database, because this is only a simple simulation software | high | 1 | Make sure all of information about bills and price should be stored in the document with “.txt”, besides, all of tasks should be operated with these text document. |  | 2020.3.20 | 2020.4.17